## Sheet1
Project | Scope | Dev |  |  | Effort Needed(days)
|  | Mobile | Web | Backend | Mobile | Web | Backend
Attendance,Leave & Location Tracking | The Employee reports sign-in ,Checkin and signout and capure the time and location and mark them | done | page completed, need to work in location and time | yet to work | - | 0.5 | 2
Attendance,Leave & Location Tracking | The Employee Leave,week-off,combo off,OD applied and approved in HRMS | leave apply from done, Approved process need to work | leave apply form done, Approved process need to work | yet to work | 2 | 2 | 2
Attendance,Leave & Location Tracking | The Check-in time,location and the travel trip distance from the previous check-in captured so that manager keeps in track | done | yet to work | yet to work | - | 0.5 | 2.5
Travel Convenience | The employee reports check-in via mobile app | done | done | yet to work | - | - | 0.5
Travel Convenience | The HR team can track location&time and record trips with distance and calculate the travel conveyance based on that | Except travel conveyance others done | yet to work | yet to work | 0.5 | 1 | 1
Travel Convenience | Any Regularization to be done, Manager has to approve,and HR aduit the same before the conveyance get released to the employee | yet to work | yet to work | yet to work | 2 | 2 | 2
Report Generation | Employees Personal details ,attendance history,check-in history,pay structre , conveyance history can be viewed and downloded in excel | yet to work | yet to work | yet to work | 2 | 2 | 2.5
Loan & Advance | Requests for loans and advances fron the employye are tracked and updated on the HRMS which allows the manager to track and updated the details | yet to work | yet to work | yet to work | 3 | 3 | 2.5
Recruitment & Onboardings | Uploading the candidates resumes and scheduling interviews for them | yet to work | yet to work | yet to work | 2 | 2 | 3
Recruitment & Onboardings | shortlisting candidates for further process | yet to work | yet to work | yet to work | 2 | 2 | 2
Recruitment & Onboardings | issue the offical offer letter to the selected candidates | yet to work | yet to work | yet to work | 2 | 2 | 3
Employee Profile Management | the Employees profile will be captured with a necessary attachement required (DL,Aadhar,Photo) | need to work attachements | done | yet to work | 1 | - | 1
Employee Profile Management | Employees date of joining,designation,reporting manager,department | done | done | yet to work | - | - | 1
Salary structre & Performance Appraisal | Employee current salary with break ups | yet to work | yet to work | yet to work | 2 | 2 | 2
Salary structre & Performance Appraisal | performance appraisal with date ,designation and salary hike for the current year and previous year | yet to work | yet to work | yet to work | 2 | 2 | 2
Payslip Management | payslip are generated upon request from the employee via payroll | yet to work | yet to work | yet to work | 1 | 1 | 2
Payslip Management | the manager approve the request in the HRM | yet to work | yet to work | yet to work | 1 | 1 | 2
Payslip Management | the HR shall provide the final appoval and the payslip in PDF format shall be generated by system and send to employyee via Email (cc:HR team) | yet to work | yet to work | payslip pdf generated, need to work in Email | 1 | 1 | 2
|  |  |  | Total | 23.5 | 24 | 35